## Slide 1
HAQAA3 Agency Reviews Training: Site Visit Logistics
Joan Akua Iyoha &
Josiane Taley Sossou
(PAQAA, TU, AAU)

## Slide 2: Overview of Site Visit Logistics Aperçu de la Logistique de la Visite
Purpose: Ensure smooth, well‑coordinated national visit
Three key actors: Agency, HAQAA3 interim TU Coordinator, & Experts
Focus: Practical arrangements, roles, and cost coverage
Assurer une visite nationale fluide et coordonnée
Trois acteurs clés : l’Agence et le Coordinateur de l’unité technique intérimaire de HAQAA3
Focus sur les rôles, arrangements et couverture des coûts

## Slide 3
Agency Responsibilities – Part 1
Responsabilités de l’Agence – Partie 1
Aider le coordonnateur à organiser l’hébergement, des repas et des visas pour les experts
Fournir un transport local (si nécessaire)
Mettre à disposition une salle de réunion appropriée
Support coordination in arranging accommodation, meals and visa for experts
Provide local transportation for experts from hotel to the agency and back
Liaise with the panel secretary to finalize the schedule
Invite interviewees, brief them, and arrange their local transport as needed

## Slide 4
Agency Responsibilities – Part 2
Responsabilités de l’Agence – Partie 2
Provide a suitable meeting room at agency premises or other venue (agency covers extra costs)
Enable hybrid interviews where necessary
Respect confidentiality: no video/sound recording; no extra people allowed
Provide refreshment (lunch) for the panel
Assurer toutes les dispositions techniques nécessaires à la visite.
Permettre les entretiens hybrides si nécessaire.
Respecter la confidentialité : pas d'enregistrement vidéo/audio ; aucune personne supplémentaire autorisée.
Inviter les personnes interrogées, les informer et organiser leur transport local si nécessaire.

## Slide 5
Responsabilités du Coordinateur
Coordinator Responsibilities
- Organiser les voyages internationaux
Réserver l’hébergement avec l’appui de l’agence
Superviser le développement de l’agenda
Disponible à distance pendant la visite
l’unite de coordination sera physiquement represente lors de la visite du site en tant que observateur.
Arrange experts’ international travel
Book experts’ accommodation with the support of the agencies
Liaise with agencies regarding local transportation to and from the venue
Oversee agenda development process
The coordinating unit will be physically present during site visit exercise as an observer

## Slide 6: Experts Responsibilities
Submit passport bio-data page and confirm full legal name within the agreed timeline.
Liaise with the PAQAA Technical Unit on all technical aspects of the assignment.
Review and approve proposed flight itineraries within stated deadlines.
Confirm travel dates, arrival, and departure details once shared.
Communicate any changes or constraints affecting travel or participation promptly.
Responsabilités des experts
Soumettre la page des données biographiques du passeport et confirmer le nom légal complet dans les délais convenus.
Assurer la liaison avec l'unité technique de la PAQAA pour tous les aspects techniques de la mission.
Examiner et approuver les itinéraires de vol proposés dans les délais impartis.
Confirmer les dates de voyage, les détails d'arrivée et de départ une fois communiqués.
Communiquer rapidement tout changement ou contrainte affectant le voyage ou la participation.

## Slide 7
Costs Covered by HAQAA3
Coûts Couverts par HAQAA3
Rémunération des experts
Voyages internationaux
Hébergement des expert
Repas principaux (petit-déjeuner, déjeuner, dîner)
Experts’ fees (Honorarium)
International travel for experts (including related expenses)
Accommodation for experts
Main meals: breakfast and dinner

## Slide 8
Facteurs clés du succès
Key Success Factors
Timely communication
Clear schedule shared early
Prepared interviewees
Smooth logistics and flow of meetings
Strict respect for confidentiality rules
Communication dans les délais impartis
Calendrier clair communiqué à l'avance
Candidats bien préparés
Logistique et déroulement des entretiens sans problème
Respect strict des règles de confidentialité

## Slide 9
Liste de contrôle de planification et de coordination de la visite de site au Lesotho
Site Visit Planning Checklist -Lesotho
Dates: 23–26 February 2026
Arrival: 23 February 2026
Site Visits: 24–25 February & morning of 26 February 2026
Departure: 26 February 2026 (or 27 February 2026 if no suitable flights)
Planning Start Date: 14 January 2026
Dates : 23–26 février 2026
Arrivée : 23 février 2026
Visites de site : 24–25 février et matinée du 26 février 2026
Départ : 26 février 2026 (ou le 27 février 2026 en l’absence de vols appropriés)
Date de début de la planification : 14 janvier 2026

## Slide 10
Progress of the Preparation of the Site Visit-Lesotho
No. | Task Description | Exact Date(s) | Priority | Status
1 | Finalize site visit dates (arrival & departure) | 14 January 2026 | High | ✅ Done
2 | Notify internal AAU leadership and relevant units of the proposed site visit | 14–15 January 2026 | High | ✅ Done
3 | Send communication to Experts/Panel Members requesting passport biodata | 15 January 2026 | High | ✅ Done
4 | Receive and validate the experts’ passport biodata | 16–17 January 2026 | High | ✅ Done
5 | Contact travel agents for flight itineraries and best pricing | 17–20 January 2026 | High | ✅ Done
6 | Liaise with the host Agency for official invitation letters (visa purposes) | 20–22 January 2026 | High | ✅ Done
7 | Confirm visa requirements and timelines for Experts | 22–24 January 2026 | High | ✅ Done
8 | Finalize proposed hotels with the host Agency (cost, proximity & services) | 24–27 January 2026 | High | ✅ Done

## Slide 11
Progress of the Preparation of the Site Visit-Lesotho
No. | Task Description | Exact Date(s) | Priority | Status
9 | Share draft travel itinerary and declaration forms with Experts for review | 28 January 2026 | High | ✅ Done
10 | Receive Experts’ confirmations and travel approvals | 29–30 January 2026 | High | ✅ Done
11 | Proceed with ticketing (arrival: 23 Feb / departure: 26 or 27 Feb) | 31 January – 3 February 2026 | High | ✅ Done
12 | Share confirmed tickets with Experts and provide AAU invitation letter (and Centre invitation, if available) | 3–4 February 2026 | High | ✅ Done
13 | Secure hotel reservations in line with confirmed flight dates | 4–5 February 2026 | High | ✅ Done
14 | Coordinate airport pick-up and drop-off arrangements with the host Agency | 6–10 February 2026 | High | ✅ Done
15 | Develop a detailed travel tracking table (arrival & departure logistics) | 10 February 2026 | Medium | ✅ Done

## Slide 12
Progress of the Preparation of the Site Visit-Lesotho
No. | Task Description | Date | Priority | Status
23 | Prepare consolidated site visit budget | 5–7 February 2026 | High | ✅ Done
24 | Confirm and validate all expenditures | 7–10 February 2026 | High | ✅ Done
25 | Prepare per diem, honorarium, and allowances (if applicable) | 10–14 February 2026 | Medium | 🔄 Pending
26 | Compile site visit documentation pack (agenda, contacts, letters) | 17–20 February 2026 | Medium | 🔄 Pending

## Slide 13
Progress of the Preparation of the Site Visit-Lesotho
No. | Activity | Date | Priority | Status
16 | Arrival of Experts in Maseru, Lesotho | 23 February 2026 | High | 🔄 Scheduled
17 | Internal briefing and logistics check | Evening, 23 February 2026 | Medium | 🔄 Scheduled
18 | Full site visit activities (Day 1) | 24 February 2026 | High | 🔄 Scheduled
19 | Full site visit activities (Day 2) | 25 February 2026 | High | 🔄 Scheduled
20 | Final site visit activities and wrap-up meeting (morning) | 26 February 2026 | High | 🔄 Scheduled
21 | Departure of Experts (preferred) | Afternoon/Evening, 26 February 2026 | High | 🔄 Scheduled
22 | Contingency departure date (if no suitable flights) | 27 February 2026 | Medium | 🔄 Planned

## Slide 14
THANK YOU!​
MERCI!
More information at
Pour plus d'informations visitez
www.haqaa3.obreal.org